{"text_format":"2","workbook":"xlsx","n_sheets":3,"sheets":["Sheet2","仓储管理","售后服务"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":1,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Sheet2","index":0,"n_rows":29,"n_cols":17,"rows_kept":29,"cut":false,"hidden":true,"merged":[[0,0,0,16],[1,5,1,6],[1,7,1,8],[1,9,1,10],[1,11,1,13],[1,14,1,16],[1,0,2,0],[1,1,2,1],[1,2,2,2],[1,3,2,3],[1,4,2,4],[3,1,5,1],[6,1,15,1],[16,1,18,1],[19,1,24,1],[25,1,28,1]]}
["仓储管理功能开发工作计划（24.02-24.03）-总体负责人：刘战洪"]
["序号","模块名称","工作名称","多端","角色","计划",null,"前端",null,"后台",null,"一轮测试",null,null,"二轮测试"]
[{"$nulls":5},"开始日期","结束日期","负责人","完成时间","负责人","完成时间","负责人","完成时间","测试结果","负责人","完成时间","测试结果"]
[1,"采购","采购单","PC","采购员","2024.02.28","2024.02.29","郭兴","2024.02.29","王鹏飞"]
[2,null,"采购退货","PC","采购员","2024.03.01","2024.03.04","郭兴","2024.03.04","王鹏飞"]
[3,null,"供应商管理","PC","采购员","2024.03.05","2024.03.05","郭兴","2024.03.05","王鹏飞"]
[4,"仓库","库存查询","PC","库管员","2024.03.06","2024.03.06","郭兴","2024.03.06","王鹏飞"]
[5,null,"入库","PC","库管员","2024.03.07","2024.03.07","郭兴","2024.03.07","王鹏飞"]
[6,null,"出库","PC","库管员","2024.03.08","2024.03.08","郭兴","2024.03.08","王鹏飞"]
[7,null,"退库","PC","库管员","2024.03.08","2024.03.08","郭兴","2024.03.08","王鹏飞"]
[8,null,"出入库查询","PC","库管员","2024.03.09","2024.03.11","郭兴","2024.03.11","王鹏飞"]
[9,null,"盘库","PC","库管员","2024.03.12","2024.03.12","郭兴","2024.03.12","王鹏飞"]
[10,null,"调拨","PC","库管员","2024.03.13","2024.03.13","郭兴","2024.03.13","王鹏飞"]
[11,null,"调价","PC","库管员","2024.03.14","2024.03.14","郭兴","2024.03.14","王鹏飞"]
[12,null,"库龄查询","PC","库管员","2024.03.09","2024.03.11","郭兴","2024.03.11","王鹏飞"]
[13,null,"库存结转","PC","库管员","2024.03.09","2024.03.11","郭兴","2024.03.11","王鹏飞"]
[14,"报表","采购报表","PC",null,"2024.03.15","2024.03.18","郭兴","2024.03.18","王鹏飞"]
[null,null,"库存报表","PC",null,"2024.03.19","2024.03.20","郭兴","2024.03.20","王鹏飞"]
[15,null,"销售报表","PC",null,"2024.03.19","2024.03.20","郭兴","2024.03.20","王鹏飞"]
[16,"基础信息","商品管理","PC","库管员","2024.02.23","2024.02.26","郭兴","2024.02.26","王鹏飞"]
[17,null,"商品类别管理","PC","库管员","2024.02.23","2024.02.26","郭兴","2024.02.26","王鹏飞"]
[18,null,"品牌管理","PC","库管员","2024.02.23","2024.02.26","郭兴","2024.02.26","王鹏飞"]
[19,null,"厂家管理","PC","库管员","2024.02.27","2024.02.27","郭兴","2024.02.27","王鹏飞"]
[20,null,"仓库管理","PC","库管员","2024.02.27","2024.02.27","郭兴","2024.02.27","王鹏飞"]
[21,null,"库区管理","PC","库管员","2024.02.27","2024.02.27","郭兴","2024.02.27","王鹏飞"]
[22,"财务","供应商账户-采购应付","PC",null,"2024.03.21","2024.03.21","郭兴","2024.03.21","王鹏飞"]
[23,null,"供应商账户-核销单","PC",null,"2024.03.22","2024.03.22","郭兴","2024.03.22","王鹏飞"]
[24,null,"客户账户-客户应收","PC",null,"2024.03.25","2024.03.25","郭兴","2024.03.25","王鹏飞"]
[25,null,"客户账户-核销单","PC",null,"2024.03.26","2024.03.26","郭兴","2024.03.26","王鹏飞"]

{"sheet":"仓储管理","index":1,"n_rows":32,"n_cols":18,"rows_kept":32,"cut":false,"hidden":true,"merged":[[1,1,1,17],[2,6,2,7],[2,8,2,9],[2,10,2,11],[2,12,2,14],[2,15,2,17],[2,1,3,1],[2,2,3,2],[2,3,3,3],[2,4,3,4],[2,5,3,5],[4,2,6,2],[7,2,17,2],[18,2,20,2],[21,2,27,2],[28,2,31,2],[28,6,29,6],[30,6,31,6],[4,7,6,7],[7,7,12,7],[15,7,17,7],[18,7,20,7],[21,7,27,7],[28,7,29,7],[30,7,31,7],[4,6,6,6],[7,6,12,6],[15,6,17,6],[18,6,20,6],[21,6,27,6],[24,9,27,9],[28,9,29,9],[30,9,31,9],[4,9,6,9],[7,9,12,9],[15,9,17,9],[18,9,20,9],[21,9,23,9]]}
[]
[null,"仓储管理功能开发工作计划（24.02-24.03）-总体负责人：刘战洪"]
[null,"序号","模块名称","工作名称","多端","角色","计划",null,"前端",null,"后台",null,"一轮测试",null,null,"二轮测试"]
[{"$nulls":6},"开始日期","结束日期","负责人","完成时间","负责人","完成时间","负责人","完成时间","测试结果","负责人","完成时间","测试结果"]
[null,1,"采购","采购单","PC","采购员","2024.03.06","2024.03.08","郭兴","2024.03.08","王鹏飞"]
[null,2,null,"采购退货","PC","采购员",null,null,"郭兴",null,"王鹏飞"]
[null,3,null,"供应商管理","PC","采购员",null,null,"郭兴",null,"王鹏飞"]
[null,4,"仓库","库存查询","PC","库管员","2024.02.28","2024.03.04","郭兴","2024.03.04","王鹏飞"]
[null,null,null,"收货",{"$nulls":4},"郭兴",null,"王鹏飞"]
[null,5,null,"入库","PC","库管员",null,null,"郭兴",null,"王鹏飞"]
[null,6,null,"出库","PC","库管员",null,null,"郭兴",null,"王鹏飞"]
[null,7,null,"退库","PC","库管员",null,null,"郭兴",null,"王鹏飞"]
[null,8,null,"出入库查询","PC","库管员",null,null,"郭兴",null,"王鹏飞"]
[null,9,null,"盘库","PC","库管员","2024.03.14","2024.03.14","郭兴","2024.03.14"]
[null,10,null,"调拨","PC","库管员","2024.03.05","2024.03.05","郭兴","2024.03.05","王鹏飞"]
[null,11,null,"调价","PC","库管员"]
[null,12,null,"库龄查询","PC","库管员"]
[null,13,null,"库存结转","PC","库管员"]
[null,14,"报表","采购报表","PC",null,"2024.03.15","2024.03.19",null,"2024.03.19"]
[null,15,null,"库存报表","PC"]
[null,16,null,"销售报表","PC"]
[null,17,"基础信息","商品管理","PC","库管员","2024.02.23","2024.02.27","郭兴","2024.02.26","王鹏飞"]
[null,18,null,"商品类别管理","PC","库管员",null,null,"郭兴",null,"王鹏飞"]
[null,19,null,"品牌管理","PC","库管员",null,null,"郭兴",null,"王鹏飞"]
[null,20,null,"厂家管理","PC","库管员",null,null,"郭兴","2024.02.27","王鹏飞"]
[null,21,null,"仓库管理","PC","库管员",null,null,"郭兴",null,"王鹏飞"]
[null,22,null,"库区管理","PC","库管员",null,null,"郭兴",null,"王鹏飞"]
[null,23,null,"货架管理","PC","库管员",null,null,"郭兴",null,"王鹏飞"]
[null,24,"财务","供应商账户-采购应付","PC",null,"2024.03.12","2024.03.13","郭兴","2024.03.13","王鹏飞"]
[null,25,null,"供应商账户-核销单","PC",null,null,null,"郭兴",null,"王鹏飞"]
[null,26,null,"客户账户-客户应收","PC",null,"2024.03.09","2024.03.11","郭兴","2024.03.11","王鹏飞"]
[null,27,null,"客户账户-核销单","PC",null,null,null,"郭兴",null,"王鹏飞"]

{"sheet":"售后服务","index":2,"n_rows":57,"n_cols":18,"rows_kept":57,"cut":false,"hidden":false,"merged":[[1,1,1,17],[2,1,3,1],[2,2,3,2],[2,3,3,3],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,10,2,11],[2,12,2,14],[36,2,48,2],[33,2,35,2],[56,1,56,17],[53,2,54,2],[2,15,2,17],[4,2,12,2],[13,2,15,2],[49,2,52,2],[16,2,31,2]]}
[]
[null,"售后服务管理功能开发工作计划（24.03）"]
[null,"序号","模块名称","工作名称","多端","角色","计划",null,"前端",null,"后台",null,"一轮测试",null,null,"二轮测试"]
[{"$nulls":6},"开始日期","结束日期","负责人","完成时间","负责人","完成时间","负责人","完成时间","测试结果","负责人","完成时间","测试结果"]
[null,1,"业务","预约登记","PC",null,"2024.03.11","2024.03.13","张磊","2024.03.13","樊宗哲","2024.03.11"]
[null,2,null,"创建工单","PC",null,"2024.03.12","2024.03.15","张磊","2024.03.15","樊宗哲","2024.03.13"]
[null,3,null,"工单查询","PC",null,"2024.03.14","2024.03.19","张磊","2024.03.19","樊宗哲","2024.03.14"]
[null,4,null,"分派工单","PC",null,"2024.03.08","2024.03.21","张磊","2024.03.21","李高德","2024.03.08"]
[null,5,null,"竣工质检","PC",null,"2024.03.08","2024.03.21","张磊","2024.03.21","李高德","2024.03.08"]
[null,6,null,"工单结算","PC",null,"2024.03.11","2024.03.21","张磊","2024.03.21","李高德","2024.03.11"]
[null,7,null,"返修退货（退货单）","PC",null,"2024.03.12","2024.03.29","张磊","2024.03.29","李高德","2024.03.12"]
[null,8,null,"客户回访","PC",null,"2024.03.11","2024.03.29","张磊","2024.03.29","李高德","2024.03.11"]
[null,9,null,"销售单","PC",null,"2024.03.14","2024.03.19","张磊","2024.03.19","樊宗哲","2024.03.15"]
[null,10,"采购","采购单","PC","采购员","2024.03.06","2024.03.08","郭兴","2024.03.08","王鹏飞","2024.03.06"]
[null,11,null,"采购退货","PC","采购员","2024.03.07","2024.03.08","郭兴","2024.03.08","王鹏飞","2024.03.07"]
[null,12,null,"供应商管理","PC","采购员","2024.03.08","2024.03.08","郭兴","2024.03.08","王鹏飞","2024.03.08"]
[null,13,"仓库","库存查询","PC","库管员","2024.02.28","2024.02.28","郭兴","2024.03.04","王鹏飞","2024.02.28"]
[null,14,null,"收货","PC","库管员","2024.02.29","2024.02.29","郭兴","2024.03.04","王鹏飞","2024.02.29"]
[null,15,null,"入库","PC","库管员","2024.02.29","2024.02.29","郭兴","2024.03.04","王鹏飞","2024.02.29"]
[null,16,null,"出库","PC","库管员","2024.03.01","2024.03.01","郭兴","2024.03.04","王鹏飞","2024.03.01"]
[null,17,null,"退库","PC","库管员","2024.03.01","2024.03.01","郭兴","2024.03.04","王鹏飞","2024.03.01"]
[null,18,null,"出入库查询","PC","库管员","2024.03.04","2024.03.04","郭兴","2024.03.04","王鹏飞","2024.03.04"]
[null,19,null,"盘库","PC","库管员","2024.03.15","2024.03.15","郭兴","2024.03.15","王鹏飞","2024.03.15"]
[null,20,null,"调拨","PC","库管员","2024.03.05","2024.03.05","郭兴","2024.03.05","王鹏飞","2024.03.05"]
[null,21,null,"定/调价","PC","库管员","2024.03.14","2024.03.19","郭兴","2024.03.19","底孟哲","2024.03.14"]
[null,22,null,"库龄查询","PC","库管员","2024.03.11","2024.03.15","郭兴","2024.03.15","底孟哲","2024.03.11"]
[null,23,null,"库存结转","PC","库管员","2024.03.11","2024.03.15","郭兴","2024.03.15","底孟哲","2024.03.11"]
[null,24,null,"维修领料","PC",null,"2024.03.07","2024.03.25","张磊","2024.03.25","底孟哲","2024.03.08"]
[null,25,null,"待回收旧件列表","PC",null,"2024.03.12","2024.03.27","张磊","2024.03.27","底孟哲","2024.03.12"]
[null,26,null,"旧件入库","PC",null,"2024.03.12","2024.03.27","张磊","2024.03.27","底孟哲","2024.03.12"]
[null,27,null,"旧件出库","PC",null,"2024.03.13","2024.03.27","张磊","2024.03.27","底孟哲","2024.03.13"]
[null,28,null,"旧件库存","PC",null,"2024.03.13","2024.03.27","张磊","2024.03.27","底孟哲","2024.03.13"]
[null,29,"厂家","保内提报","PC",null,"2024.03.15","2024.04.01","张磊","2024.04.01","底孟哲","2024.03.18"]
[null,30,"报表","采购报表","PC",null,"2024.03.18","2024.03.19","郭兴","2024.03.19","王鹏飞","2024.03.19"]
[null,31,null,"库存报表","PC",null,"2024.03.19","2024.04.05","张磊","2024.04.05","底孟哲","2024.03.20"]
[null,32,null,"销售报表","PC",null,"2024.03.18","2024.04.05","张磊","2024.04.05","樊宗哲","2024.03.19"]
[null,33,"基础信息","商品管理","PC","库管员","2024.02.23","2024.02.23","郭兴","2024.02.23","王鹏飞","2024.02.23"]
[null,34,null,"商品类别管理","PC","库管员","2024.02.23","2024.02.23","郭兴","2024.02.23","王鹏飞","2024.02.23"]
[null,35,null,"品牌管理","PC","库管员","2024.02.26","2024.02.26","郭兴","2024.02.26","王鹏飞","2024.02.26"]
[null,36,null,"厂家管理","PC","库管员","2024.02.26","2024.02.26","郭兴","2024.02.26","王鹏飞","2024.02.26"]
[null,37,null,"仓库管理","PC","库管员","2024.02.27","2024.02.27","郭兴","2024.02.27","王鹏飞","2024.02.27"]
[null,38,null,"库区管理","PC","库管员","2024.02.27","2024.02.27","郭兴","2024.02.27","王鹏飞","2024.02.27"]
[null,39,null,"货架管理","PC","库管员","2024.02.27","2024.02.27","郭兴","2024.02.27","王鹏飞","2024.02.27"]
[null,40,null,"维修项目管理","PC",null,"2024.03.07","2024.03.11","张磊","2024.03.11","樊宗哲","2024.03.07"]
[null,41,null,"附加项目管理","PC",null,"2024.03.07","2024.03.11","张磊","2024.03.11","樊宗哲","2024.03.07"]
[null,42,null,"套餐管理","PC",null,"2024.03.08","2024.03.12","张磊","2024.03.12","樊宗哲","2024.03.08"]
[null,43,null,"工种管理","PC",null,"2024.03.07","2024.03.08","张磊","2024.03.08","李高德","2024.03.07"]
[null,44,null,"科目管理","PC",null,"2024.03.07","2024.03.08","张磊","2024.03.08","李高德","2024.03.07"]
[null,45,null,"班组管理","PC",null,"2024.03.07","2024.03.08","张磊","2024.03.08","李高德","2024.03.07"]
[null,46,"财务","供应商账户-采购应付","PC",null,"2024.03.13","2024.03.14","郭兴","2024.03.14","王鹏飞","2024.03.13"]
[null,47,null,"供应商账户-核销单","PC",null,"2024.03.14","2024.03.14","郭兴","2024.03.14","王鹏飞","2024.03.14"]
[null,48,null,"客户账户-客户应收","PC",null,"2024.03.11","2024.03.12","郭兴","2024.03.12","王鹏飞","2024.03.11"]
[null,49,null,"客户账户-核销单","PC",null,"2024.03.12","2024.03.12","郭兴","2024.03.12","王鹏飞","2024.03.12"]
[null,50,"其他","创建售后服务微服务yxt-as",{"$nulls":6},"底孟哲","2024.03.06"]
[null,51,null,"创建售后服务前端项目yxt-as-ui",{"$nulls":4},"张磊","2024.03.06"]
[]
[null,"注：标识灰色背景的为仓储管理项目中的功能。"]